## Slide 1
Home Office Assurance Toolkit
Portfolio and Project Delivery Directorate (PPD)
August 2018, version 1.2
Slide 1
Home Office Risk Assurance Reviews
Introduction
Slide 2
Assurance and the Project Delivery Lifecycle
Slide 3
Gateway Reviews: Milestone Assurance
Slide 4
Gateway Reviews: Strategic Assurance
Slides 5
Home Office Readiness Assessments
Slide 6
Home Office and IPA Additional Assurance Interventions
Slide 7
Slide 8
Project Internal: First Line of Assurance

## Slide 2: Introduction
This toolkit summarises the assurance interventions available to projects and programmes in the Home Office
The aim of project assurance interventions and reviews is to test whether a project is delivering to agreed time, cost and quality. Other assurance activities can focus on narrower elements of a project’s work, for example, risk management or stakeholder engagement.
Home Office programmes and projects are subject to the ‘three lines of assurance’ model as set out in the draft Infrastructure and Projects Authority (IPA) Functional Standards for Project Delivery; the SROs are accountable for ensuring that appropriate assurance arrangements are in place:
  1st line of assurance; internal to the project, undertaken by management team and business area portfolio management.
  2nd line of assurance; internal to the department, undertaken by HO assurance providers (includes PPD, Commercial Directorate, and Digital, Data and Technology (DDaT)).
  3rd line Assurance; undertaken by corporate or external assurance providers (includes Government Internal Audit Agency (GIAA), IPA, Government Digital Service (GDS), Her Majesty’s Treasury (HMT) and National Audit Office (NAO)). What constitutes 3rd line of assurance interventions will depend on the complexity of the project; for instance smaller projects are unlikely to be subject to external assurance.
The Home Office approach to assurance is detailed in the Home Office’s Integrated Assurance and Approval Strategy and associated assurance guidance.
Assurance interventions include the OGC Gateway™ assurance process and assurance interventions that can be tailored and applied proportionately to a project depending on its size, risk, nature and requirements. These include
  Readiness assessments
  risk assurance interventions,
  Additional assurance interventions, and
  project internal assurance.
This toolkit provides an overview of the various assurance interventions including activities that should be in place within projects to provide internal 1st line of assurance.

## Slide 3: Assurance Interventions and the Project Delivery Lifecycle
Feasibility (Idea)
Appraise and Select (Initiation)
Define (Investment approval)
Deliver
Operate, embed & close
Benefits realisation
Gate 5 (operations), Exit Review
Gateway 4 Readiness for service
Gate 2 Delivery Strategy
Project Validation Review (PVR)
Gate 0 Review
PAR or Gate 0
PAR or Gate 0
Project Validation Review (PVR)
Gate 1 Business Justification
Gate 3 Investment Decision
Project Assessment (PAR) or Gate 0 (strategic Assessment)
PAR or Gate 0
Gate 0 with focus on benefits realisation
Gate 5 (benefits realisation)
Gateway: Milestone Assurance
Gateway: Strategic and Programme
Assurance
Readiness Assessments
Tailored Assurance Interventions
Risk Assurance Interventions
Project Internal Assurance
Health Check, Critical Friend, Assurance of Plans, Technical Assurance, Cluster of (technical) Reviews
Facilitated events such as Devil’s Advocate, Black Swan, Risk Identification Techniques, ‘Pre Mortem’
Review by Local Business Design Authority/Business Analyst, internal project governance, proactive risk and issues management, dashboard reporting and project self-assessment
Notes: We have mapped the assurance reviews and HO approval points on the project delivery lifecycle. As you can see there are reviews for all the major milestones or stages. For projects with a long delivery phase you would expect to have an annual review such as a PAR or a health check to make sure that reviews are on track.
There may also be other bespoke assurance interventions along the way and it’s all underpinned by the first line of assurance
This schematic could help you to construct the basis of an IAAP for your programme or project.

## Slide 4: Gateway Reviews: Milestone Assurance
Review | Purpose | Format | Output
Gate 1 | Business Justification: This is the first project review, which investigates the Strategic Business Case and proposed way forward to confirm that the project is achievable and likely to deliver what is required. The review checks that: stakeholders approve the intended benefits from the project linkage with programme and organisational objectives is clear the optimum balance of cost, benefits and risk has been identified. | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Gate 2 | Delivery Strategy: This review investigates the assumptions in the Outline Business Case and proposed approach for delivering the project. If there is a procurement, the delivery strategy will include details of the sourcing options, proposed procurement route and supporting information. The review will also check that plans for implementation are in place. | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Gate 3 | Investment Decision: This review investigates the Full Business Case and the governance arrangements for the investment decision to confirm that the project is still required, affordable and achievable. The review also checks that implementation plans are robust. | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Gate 4 | Readiness for Service: his review investigates the organisation’s readiness to make the transition from the specification/solution to implementation; where appropriate it will assess the capabilities of delivery partners and service providers. The review also confirms that ownership of the project is clearly identified after handover to operational services | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Gate 5 | Operations Overview and Benefits Realisation: This review confirms that the benefits set out in the Business Case are being achieved and that the operational service (or facility) is running smoothly. The review is repeated throughout the life of the service, with the first review typically 6-12 months after handover to the new owner and a final review shortly before the end of a service contract. The review can also be used on a one-off basis, to check that a project has delivered its intended outputs. | Document review, interviews with key stakeholders over 2 to 3 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Exit Review | Exit Reviews confirm that there is a realistic and agreed overall programme closure plan, that there will be appropriate, and agreed, post-closure governance to monitor any continuing spend and the delivery of benefits; that all actions arising from previous assurance recommendations have been completed appropriately or an agreed action plan is in place and that the programme has sufficiently delivered the policy objectives originally agreed. | Document review, interview with some key stakeholders up to 2 days, 1 day report writing | Report and Delivery Confidence

## Slide 5: Gateway Reviews: Strategic Assurance
Review | Purpose | Format | Output
Project Validation Review (PVR) | The Project Validation Review should be applied at the initiation of any change project, preferably sufficiently early to ensure its findings can be reflected in the initial business case. The short, usually workshop-based, review enables: The alignment of the project’s objectives with organisation’s wider change portfolio; Support to the project being set-up (to deliver to time, quality, and budget) before fully developing its strategic options (in its feasibility/discovery stage); The sharing of views, opportunities and risks with key stakeholders, and Consideration of early strategic delivery options and standards. | Document review, workshops with stakeholders over 1 day, 1 day report writing | Report
Project Assessment Review (PAR) | The Project Assessment Review is a flexible assurance review used whenever bespoke Terms of Reference are required to meet the specific assurance needs of a project or programme. Examples of what a PAR can provide include: A deeper investigation of known issue areas or analysis of a project in difficulty to determine the root cause(s) of failure, A broad strategic analysis across a number of complex issues and/or cross-government dependencies, Identification of potential cost savings. | Document review, issues workshop if required and interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence
Gate 0 | Strategic Assessment: this is a programme-only review that sets the programme in the wider policy or corporate context. This review investigates the direction and planned outcomes of the programme, together with the progress of its constituent projects. It can be applied to any type of programme, including policy and organisational change. The review is repeated throughout the life of the programme from start-up to closure. | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing, site visit (if appropriate) | Report and Delivery Confidence

## Slide 6: Home Office Readiness Assessments
Stage | Purpose | Format | Output
Ideas / Initiation Phase | The Initiation Readiness Assessment supports project initiation to help the development of projects ahead of the formal assurance and approval process. It replaces the PPD whiteboard. | 90 minute workshop, examining: Strategic Fit Benefits Affordability Deliverability | Notes of initiative, decisions, key issues, actions Recommendation for portfolio adoption/tier Integrated assurance and approval approach Detailed approach to next approval point Initial contact with key assurance and scrutineer colleagues
Delivery Phase | The Delivery Readiness Assessment provides deeper scrutiny of investment proposals before consideration by the Portfolio Investment and Change (PIC) Committee. | 90 minute workshop, focusing on obtaining the necessary assurance for PIC on the reliability of the programme’s cost estimates and profile, programme specific issues and that the optimum approach is being pursued to meet its priority requirements and to support any discussions on affordability. | Approval to proceed to PIC Notes of initiative, decisions, key issues, actions High level Investment Appraisal including potential PIC recommendations Confirmed Integrated Assurance and Approval Plan Detailed approach to next approval point
BaU Transition/ Closure Phase | The Transition to BaU/Closure Readiness Assessment assures plans for closure and transition to BaU before PIC agrees closure (transition readiness assessment sits alongside other assurance interventions at closure and projects should select the most appropriate assurance intervention(s) in consultation with the PPD assurance team) | 90 minute workshop, confirming: Readiness for closure Transition plans Resource hand back plans Asset handback plans BAU Arrangements | Closure plan, including PIC appearance timing Resource (finance and people) hand back plans Notes of initiative, decisions, key issues, actions Lessons learnt and PIR arrangements
Readiness assessments aim to:
  Bring together key partners from business areas and Corporate Services for an open discussion
  Explore key issues appropriate for the project stage before formal assurance and approval
  Provide support for projects to address issues directly with key partners

## Slide 7: Home Office and IPA Additional Assurance Interventions
Review | Purpose | Format | Output
Health Check | A Health Check assure the SRO that the project is on the right track regarding documentation, stakeholder engagement etc. | Document review, interviews with key stakeholders over 2 to 4 days, 1 day report writing | Delivery confidence and recommendation
Critical Friend | A Critical Friend review examines specific areas of concern, perhaps requiring specialist skills by the reviewers e.g. IT, Commercial. To assure that the project is on track at key points and/or to provide specific insight. | Flexible interviews (e.g. an intense period over a week or could be a day here and there over a longer period) | Recommendations to the SRO
Assurance of Plans | An Assurance of Plans provides external assessment of plans e and confirms that they are realistic and all dependencies have been captured | Review of planning by an independent planning specialist | Report and recommendations
Technical Assurance | Technical Assurance assess a particular technical aspect of the project, e.g. Telecommunications for ESMCP, using external and independent expertise | Document review, technical review and stakeholder interviews over an agreed period; this may require buying in relevant technical expertise | Report and recommendations
Cluster of (technical) reviews | A Cluster of Reviews simultaneously assess various technical aspects of a project and bring together into a ‘review of reviews’ report led by the RTL for the technical reviews | Document review, technical reviews into various technical aspects of the project and stakeholder interviews; this may require buying in relevant technical expertise | Report and recommendations
Assurance of Action Plan (AAP) | An Assurance of Action Plan review follows an assurance review, where delivery confidence has been assessed as Red or Amber/Red. It re-assesses a Delivery Confidence Assessment in the light of actions taken. Timing-wise, this will generally be after the project has had an opportunity to plan how to address the review recommendations; this is normally within two to three months of the original review, but this may vary with the project context and circumstances. | Consideration of previous review report, action plan, documents as required; 1 day in total for interviews and report writing | Report focussing on the effectiveness of actions to address previous review recommendations and delivery confidence assessment

## Slide 8: Home Office Risk Assurance Reviews
Review | Purpose | Format | Output
‘Devil’s Advocate’ | A Devil’s Advocate challenges assumptions and plans. this can provide independent critical thought to improve decision making | Facilitated workshop; this may require buying in relevant facilitation expertise | Tested and de-risked plans
‘Pre-mortem’ session | A Pre-mortem enables decision makers and project teams to imagine that their project has failed and work back from that to identify the possible reasons why it has failed and use those to develop a more realistic project plan | Facilitated workshop for decision makers and project team; this may require buying in relevant facilitation expertise | Framework for project plan and outline risk register
Black Swan | A Black Swan event refers to a highly improbable occurrence with three characteristics: It is impossible to predict, it carries a massive impact and its shock value is stunning because people could never conceive of such an event occurring. Learning from Black Swan events is an approach to building robustness against negative events by identifying the unpredictable | Facilitated workshop; this may require buying in relevant facilitation expertise | Framework for outline risk register
Risk Identification Techniques | Risk Identification Techniques include but are not limited to; cost and time estimating, decision tree, Delphi technique, expert judgment expected monetary value analysis, interviewing, historical records and Monte Carlo Analysis | Facilitated workshop; this may require buying in relevant facilitation expertise | Framework for project plan and outline risk register
Risk assurance review | Risk Assurance Reviews provide PIC with the assurance that risks are being managed across the Home Office Change Portfolio and in line with the departmental standards set by Corporate Risk Management Team. | Review of some key relevant documents, interviews with stakeholders and report; this may require buying in relevant facilitation expertise | Recommendations to SRO

## Slide 9: Project Internal: First Line of Assurance
Activity | Purpose | Output
Local Business Design Authority/ Business Analyst review | Business Design Authorities and Business Analysts assure alignment with government policy and departmental objectives | High level design and dependency mapping
Risk register in place and risks proactively managed | Robust Risk Registers confirm that benefits can be realised and risks managed within the organisation’s risk appetite | Unviable work is terminated
Project/Programme Governance in place | Governance, management frameworks and controls are proportionate and appropriate to the work and the level of prevailing risk. | Accountabilities and responsibilities across all management levels are aligned, consistent and traceable
Resourcing Strategy | A Resource Strategy defines how work is assigned to skilled and competent people, working in multi-disciplinary teams | Resourcing strategy in place and regularly reviewed by relevant board meeting
Regular reporting to relevant board | Reporting ensures that outcomes and enabling outputs will meet the need, and be validated by stakeholders. | Decisions are made and documented, issues are flagged and acted upon
Project Self-Assessment | Project Self-Assessments should be arranged and managed by the project manager to assure a particular area of the project; they include self-assessments (using a PPD template) before major milestones and assurance interventions (such as initiation and closure) | Reports and completed self-assessment templates