## Control
Project / Programme / Workstream
DOCUMENT REFERENCE NO:
VERSION: |  |  |  | In Development
DATE OF ISSUE: | dd/mm/yyyy |  |  | For Approval
AUTHOR: | <Name> |  |  | Awaiting Approval
APPROVER: | <Entry> |  |  | Approved
STATUS: | For Approval
Completed by | Date | Changes | Update

## About
Worksheets
Gap Analysis
Principle is straight forward – ‘the difference between current and future state’
This is a simplified example, The analyst will categorise and scale as appropriate.
Assessment (ABC), Categorisation and Prompts
These two tabs include some sugested categories for investigating and grouping change impacts as well as some questions and prompts the analyst may ask
High-Level CIA
An example template provided for a whole project, view of the aggregated change impacts.
This can be drawn-up early in the lifecycle making assumptions in order to gain early insight into the likely impacts and areas affected by the proposed changes.
Detailed CIA
The example template provided is designed to give a detailed view of changes and their impacts on a business area or unit.
This could be scaled-up to include sections for each business are affected. This should be adapted and tailored according to the project.
The change lead will need to tailor and scale an analysis suitable for the nature and complexity of the project or programme.
Summary Chart
This example can be used at any stage to give a view across the whole project of the realtive priorities of change impacts.
The chart displays an assessment of liklihood and scale, for each change impact, on each group or team affected.
Change Impact Analysis
What does it cover?
Change Impact Assessments (CIAs) support the Programme and the Business to understand what effect a Project / Project release will have on the business, its users and HO customers.
The CIA builds on the change assumptions that were developed earlier, through analysing how different aspects of operations will change and what impact these changes will have on
the arrangements currently in place. It may be appropriate to develop CIAs for each of the business areas affected.
The Change Team and the Business Change Leads can then develop targeted change plans to address each impact and use the information to communicate effectively with those affected
by the changes.
Change Impact Analysis – summarised features
A series of activity not a single event - It’s a process not an event- there are a number of elements to consider- these need to be built up via a well planned process
Business owned - Gap analysis must be done with and owned by business stakeholders. Change managers facilitate, manage and influence.
A process that has structure – it cannot be contemplated until precursory information and decisions have been established, has to be objective and provides specific outputs to the change plan.
Scalable -For smaller decisions, it could be conducted as a desk exercise.
For larger or more risky decisions, it is best conducted with an experienced team, ideally with people from different functional backgrounds within the organisation
Commencing the CIA process
As with other change management techniques there is no single ‘right way’. Some relevent points:
The conduct of the process is responsibility of the Change Lead
Pre-determinants
•Case for change
•A baseline – ideally including As Is processes
•TOM (avoid being pulled into requirements gathering)
•Business ownership – especially SRO
Approach
•When / where?
•Scale, e.g. Single event, series of workshops?
•Tools to use?
Who to involve
•Must be representative across the affected business areas
•Could involve non HO staff
•Engagement which is too broad could introduce confusion
•Relative roles and responsibilities should be clear – including validation
Who to involve
There is no finite list
The need is to achieve an holistic assessment – if there is to be bias it should be weighted towards business contribution
In a mid to large project where do you draw the line? There may be a need to:
•Prioritise involvement
•Be hard nosed and decline non essential interest
•Run separate smaller sessions ?
The SRO should have final call in case of dispute
Example CIA Stakeholders:
Stage1 - Gap Analysis
Can be complex or simple
Principle is straight forward – ‘the difference between current and future state’
Start with the business view of high level/ critical impacts
Work through to detailed people and process impacts from this
Beware:
•Changes which may appear insignificant may not be - small technology change may mean big business change
•Thinking about process, technology, process in isolation
•Assuming the same gap for all stakeholders
•Strong personalities – can skew objectivity
•Polarised viewpoints
Stage 2 – Change Impact Assessment
Purpose
To take the ‘Gaps’ and assess the resultant impacts as they relate to specific groups (stakeholders)
Features
•The gaps need to be defined before ‘impacts’ can be assessed
•Enables ‘gaps’ to be broken down to understand how they impact on individual groups (which is likely to be different)
•An opportunity to start thinking about relative priorities for change interventions
•An opportunity to introduce cross referencing / audit trail
Stage 3 – Collate and prioritise
Purpose
To take the identified ‘impacts’ and break them down into equivalent change interventions
Features
•Depends on the output from ‘impact assessment’
•Identifies interventions for specific groups
•Provides an opportunity to categorise the interventions, e.g. Training, which enables allocation of ownership
•Extends cross referencing / audit trail
•Outputs will feed into the change plan (next kill session)
How might this approach be adapted for Agile?
The importance of getting it right!
•Change Impact Assessment goes beyond the practical realities of training and implementation of new processes;
it assesses how ready people are to actually make the required changes.
•If they are not ready, the end result is changes that fail to entrench:
–People cope with change rather than benefit from it
–People work around the intended changes
–Modifications to processes and systems but not behaviours
–Resistance and disinterest towards this and future changes
–A belief that change is done to them – not seen as something they influence or embrace
•Failing to assess attitude to change can mean:
–-People’s attitude to change is (more)negative
–Change plans will flounder or fail
Success checklist
Before you start
•Is the case for change clear?
•Is an SRO identified, and are they committed to the change?
•Is there a baseline (ideally including As Is processes)?
•Is the endpoint defined (ideally including a Target Operating Model)?
The CIA Process
•Is the process planned out – phases? Tools?
•Is the approach scaled to the need of the particular project?
•Is the representation correct – i.e. balanced or weighted toward the business
Managing the outcomes
•Does the SRO accept ownership (more than words alone!!)
•Are next steps clear and agreed? – i.e. Is task ownership established?
•Is it clear what interventions are recommended? – i.e. Check the language, would someone with no knowledge of the project be able to understand them.
Now
(As Is)
Future
(To Be)
Validate ‘As Is processes
Usually jointly with BAs/ system integrators
Needs to cover people, process and technology
Needs to be current and validated with the business
Establish Target Operating Model
An integrated view of how the business wants to look following the change process, incorporating people, process and technology
Identify impacts of change
Identify the impact change will have on people, process and technology
Gap Analysis
A cross sectional view of the difference between As Is and To Be
Confirm Case for change
Usually jointly with BAs/ system integrators
Needs to cover people, process and technology
Needs to be current and validated with the business
Collate and prioritise
Outline the resolution the issues in preparation for change planning
Change lifecycle
Change Impact Analysis
Typically a series of activities rather than a single event
Final Handover
Business Readiness Checklist
CIA 001
Business As Usual: Legacy in place
CIA 002
CIA 003
Change Impact Log
Training Activity
Communications Activity
SPRINT
SPRINT
SPRINT
CIA 004
SPRINT

## Gap Analysis
CHANGE MANAGEMENT - High level GAP ANALYSIS [project name]
Theme of change | As Is | To Be | Nature of difference | Stakeholders affected
PEOPLE
PROCESS
ORGANISATION
TECHNOLOGY, INFRASTRUCTURE

## ABC Assessm't
ABC Diagnostic Framework
The below is an aide memoir when undertaking a Change Impact Assessment. This is in no way exhaustive…
Architecture
Does the design of the solution require any changes to the organisational structure of business units?
If yes, which?
Are all of these accounted for in the change plan?
Does the design of the solution require any changes to roles and responsibilities within business units?
If yes, which?
Are all of these accounted for in the change plan?
Does the design of the solution require any changes to processes within business units?
If yes, which?
Are all of these accounted for in the change plan?
Will current architectural arrangements be able to support the solution when rolled out?
If not, is this in the plan?
Will all business area Management Information requirements be met by the new solution, if applicable?
If not, is this in the plan?
Are detailed success criteria / KPIs etc in place for the solution being rolled out into the product area?
If not, is this in the change plan?
Are targets in place by which delivery of the success criteria can be measured?
Are targets cascaded down to business units/teams?
If not, is this in the plan?
Are business unit/team performance measurements translated into individual measures, targets and PDRs
If not, is this in the plan?
Behaviour
Are existing staff behaviours towards change A. known and B. conducive to endurably embedding change within the business?
If no to either, are steps to improve incorporated into the plan?
Are local line leads clear about the activities and behaviours required of them to deliver change effectively?
If not, is this in the plan?
Is the impact of the strategic vision (organisational and programme / workstream / project) understood for each role in the organisation and or made clear?
If not, is this in the plan?
Communication
Is the business communicating a clear, consistent and accessible change story to all its staff? Aka compelling story?
If not, is this in the plan?
Have local leaders agreed a plan of activities they will carry out to support the change message in their business area?
If not, is this in the plan?
Is the business making effective use of all existing communications fora to emphasise the durability of the change?
If not, is this in the plan?
Development
Does the business have an effective training strategy to support change by;
a. Encouraging high performing staff to stay with the organisation, and develop those staff
b. Using the most appropriate mix of formal and informal training
c. Training all new staff in the new processes
d. Helping outgoing staff to develop their career outside the team
Execution
Is product area and programme / project /workstream governance A. clear and B. functioning?
If not, is this is the plan?
Is progress in delivering the programme being effectively reported and managed?
If not, is this is the plan?
Is the deployment plan clear and realistic?
If not, is this is the plan?
Does the deployment plan include workstreams and ensure that all are resourced?
Are plans in place to validate the assumptions underpinning benefits statements?
Is there a process in place to track benefits realisation?
If not, is this in the plan?
Do management reports include measures indicating progress made in delivering change as well as in managing BAU work?
If not, is this in the plan?
Feedback
Is an effective Business Engagement/ Agent Network in place to provide real-time feedback on how change is progressing in the business?
Will sufficient staff feedback as to the effectiveness of programme support be obtained?

## Categorisation&prompts
Below is an example categorisiation of the expected change impacts and some prompts to aid investigation into the likely impacts
Assessment Area | Assessment Area Definition | Question
Business Process Execution | Changes to the range of processes that are carried out, how they are executed and the supporting business artefacts that are required | · Are there additional process steps/activities?
· Do some process activities need to be stopped/de-commissioned?
· Are additional business artefacts (e.g. checklists, forms) required to execute the process? Are there any which need to be modified or withdrawn?
Customer Experience | Changes to what customers are expected to do, what they see or in their interactions with UKBA | · How will the customer’s experience be affected?
· What needs to be done to optimise the experience for the customer in the new environment?
· Are there any ‘equality’ issues for customers arising from the changes?
· Are there changes for Corporate Partners and any other external stakeholders?
· What customer support arrangements need to be in place in order to handle customer queries?
Legislation & Policy | The ‘rules’ framework that governs business operations | · Are there changes required to legislation and/or policy? Are actions being taken to carry these out?
Team Structures & Organisation | Changes to the ways teams and currently structured and how this will develop to reflect new business processes | · Are there changes to the overall functions and accountabilities of teams?
· Will there be any changes required to team structures?
· Will the interactions between teams change?
· Are changes required to governance arrangements and where decisions are made?
· How will the role of team management change?
Roles and Responsibilities | Changes to the way a user completes their daily work, including different processes, tasks, responsibilities, working patterns etc. | · Which roles are affected by the changes? How will this change in process affect the content of current roles?
· Will this affect which responsibilities are assigned to people?
· What do you think will be the biggest change to ways of working?
· Will the change in process affect the scope of ‘cover’ required (e.g. over more hours)?
· Will the process change affect the amount of resource required to carry out key tasks?
Culture and behaviour | Changes to the attitudes, beliefs, values and behaviour of the organisation and its staff | · What attitudinal and behavioural barriers exist that will hamper the shift to these new, more automated ways of working?
· What behaviours should be encouraged in the future in order to carry out new ways of working?
· How will managers of IPT users need to change how they manage work their teams?
Business Performance, Objectives and targets | Changes to individual or team targets and objectives, and changes to the way these are captured and calculated | · What impact will the new ways of working have on operational performance (e.g. in relation to quantity or quality of work completed)
· What will be the impact of the changes on targets set for teams and other organisational units?
· What are the measures that are applied to people’s work today and how should these change with new ways of working?
· Will managers need to use different sources of data in order to manage team and individual performance?
· What impact will the new ways of working have on the length of time required to complete pieces of work?
Skills and competencies | Changes to the skills that staff and managers currently have to do their job and how the competencies underpinning these will need to also change | · Will additional skills and knowledge need to be learnt to operate effectively in the new working environment?
· What tools are in place to assess employee skills and competencies? How will these be affected?
Workspace tools and facilities | Changes to the way people work and the environment with which they work is carried out. How this affects the tools they have for their jobs as well as what new facilities may be required to support the change | · Will there be any changes to where work is carried out (e.g. some tasks cease at one location but are concentrated at another)?
· Will there be any required changes to office space and layout?
· Is there a flexible working policy? Will flexible working be possible with this process change?
· Will there be changes to the technology (hardware & telephony) deployed on desks?
· Is there a hot desk policy or do staff have their own desks? Will this change?
· Are there any ‘equality impacts’ (e.g. for employees with a disability)?
Procedures and guidelines | Changes to the current procedures and guidelines that support the business processes and operations of the day to day tasks of all staff | · What procedures and guidance is available to staff that will need to be revised, removed or created? Will the scope of guidance available to staff change?
· Will there be any changes to where or how people access procedures and guidance? Are procedures and guidelines documented and will this change?
· Are there contingency procedures in place? How will these need to change?
· Do procedures and guidelines differ across regions? Will this change?
MI & Reporting | Changes to the information collected by managers to support the running and effective functioning of business operations | · Will different management information need to be collected?
· Are any other forms of MI captured currently? How will this change?
· How will the MI reporting process change?
· How will changes in MI affect staff?
Reward and recognition | Changes to the way that staff are rewarded and recognised for high performance in the job they do and how this is assessed and calculated | · Does what constitutes ‘success’ change in the way that staff are evaluated?
· Will there be any changes in how ‘success’ is recognised?
Contracts & Service Level Agreements with 3rd Parties | Changes to contractual agreements and service level agreements with third parties involved in carrying out the processes | · What contractual arrangements are in place currently? How will these be affected?
· What Service Level Agreements (SLAs) are in place currently? How will these be affected?
· Will additional SLAs or contractual arrangements be required?
Transitional Arrangements | ‘Interim’ changes that need to be adopted until everyone is working on IPT (and then can be stopped) | · Are there transitional ways of working that need to be introduced whilst only part of the organisation is using IPT?
· Will there be changes in the interactions between staff who are operating new ways of working and those in other parts of UKBA?
Ongoing Solution Management & Maintenance | Changes to ‘Business as Usual’ arrangements for supporting users, changing systems access and permissions, requesting changes to the solution to reflect new/changed business needs | · Will there be changes to the scope of service management support (including user help and support) and how it is provided? How will all the different types of user query be handled?
· How will changes to user access requirements be managed?
· How will solution changes be initiated by the business?
· How will solution changes be communicated and implemented?

## High-Level CIA
Example High-Level Change Impact Assessement
Programme / Project / Workstream
Criteria | Assessment Area | Impact Statement | Current Situation (Summary) | Desired Situation (Summary) | Start doing | Stop doing | Do differently
People | Roles Responsibilities Competencies Skills | Add text or 'N/A' here | Add text or 'N/A' here | Add text or 'N/A' here | Add text or 'N/A' here | Add text or 'N/A' here | Add text or 'N/A' here
Culture / Behaviours / Communications
Team Structure
Operational Support (local)
Performance, Targets and Objectives
Process | As-Is Processes / Legacy Ways of Working
To-Be Processes / New ways of working
Local guidance / procedures
Policy and Legislation
Productivity
Organisation | Headcount, corporate structure, team structures
Strategic alignment, interoperability
Financial, legal, statutory, social responsibility, political, commercial
Technology and infrastructure | Work tools (scanners, screens, etc)
Office (lay out, etc)

## Detailed CIA
Example Change Impact Assessment - Detailed
BUSINESS AREA:
Change Impact Assessment I.D. | Process Description | Change description (Who, why, what, when, where) | Overall Impact Rating | Customer Experience Impact | Business Process Execution Impact | Roles and Responsibilities Impact | Skills and Competencies Impact | Team Structure & Organisation Impact | Culture and Behaviours Impact | Reward and Recognition Impacts | Business Performance, Objectives & Targets | Workspace, Tools and Facilities | Procedures and Guidelines | Legislation and Policy | Transitional Arrangements | MI and Reporting | Contractual / SLAs inc 3rd Parties | Ongoing Soluition / Service Management | Etc.
Assessment Area Description | Process Description | Change description (Who, why, what, when, where) | 2 | Changes to what customers are expected to do, what they see or in their interactions with HO | Changes to the range of processes that are carried out, how they are executed and the supporting business artefacts that are required | Changes to the way a user completes their daily work, including different processes, tasks, responsibilities, working patterns etc. | Changes to the skills that staff and managers currently have to do their job and how the competencies underpinning these will need to also change | Changes to the ways teams and currently structured and how this will develop to reflect new business processes | Changes to the attitudes, beliefs, values and behaviour of the organisation and its staff | Changes to the way that staff are rewarded and recognised for high performance in the job they do and how this is assessed and calculated | Changes to individual or team targets and objectives, and changes to the way these are captured and calculated | Changes to the way people work and the environment with which they work is carried out. How this affects the tools they have for their jobs as well as what new facilities may be required to support the change | Changes to the current procedures and guidelines that support the business processes and operations of the day to day tasks of all staff | The ‘rules’ framework that governs business operations | ‘Interim’ changes that need to be adopted until everyone is working on IPT (and then can be stopped) | Changes to the information collected by managers to support the running and effective functioning of business operations | Changes to contractual agreements and service level agreements with third parties involved in carrying out the processes | Changes to ‘Business as Usual’ arrangements for supporting users, changing systems access and permissions, requesting changes to the solution to reflect new/changed business needs
Assessment Area Questions | Process Description | Change description (Who, why, what, when, where) | 1 | • How will the customer’s experience be affected? • What needs to be done to optimise the experience for the customer in the new environment? • Are there any ‘equality’ issues for customers arising from the changes? • Are there changes for Corporate Partners and any other external stakeholders? • What customer support arrangements need to be in place in order to handle customer queries? | • Are there additional process steps/activities? • Do some process activities need to be stopped/de-commissioned? • Are additional business artefacts (e.g. checklists, forms) required to execute the process? Are there any which need to be modified or withdrawn? | • Which roles are affected by the changes? How will this change in process affect the content of current roles? • Will this affect which responsibilities are assigned to people? • What do you think will be the biggest change to ways of working? • Will the change in process affect the scope of ‘cover’ required (e.g. over more hours)? • Will the process change affect the amount of resource required to carry out key tasks? | • Will additional skills and knowledge need to be learnt to operate effectively in the new working environment? • What tools are in place to assess employee skills and competencies? How will these be affected? | • Are there changes to the overall functions and accountabilities of teams? • Will there be any changes required to team structures? • Will the interactions between teams change? • Are changes required to governance arrangements and where decisions are made? • How will the role of team management change? | • What attitudinal and behavioural barriers exist that will hamper the shift to these new, more automated ways of working? • What behaviours should be encouraged in the future in order to carry out new ways of working? • How will managers of IPT users need to change how they manage work their teams? | • Does what constitutes ‘success’ change in the way that staff are evaluated? • Will there be any changes in how ‘success’ is recognised? | • What impact will the new ways of working have on operational performance (e.g. in relation to quantity or quality of work completed) • What will be the impact of the changes on targets set for teams and other organisational units? • What are the measures that are applied to people’s work today and how should these change with new ways of working? • Will managers need to use different sources of data in order to manage team and individual performance? • What impact will the new ways of working have on the length of time required to complete pieces of work? | • Will there be any changes to where work is carried out (e.g. some tasks cease at one location but are concentrated at another)? • Will there be any required changes to office space and layout? • Is there a flexible working policy? Will flexible working be possible with this process change? • Will there be changes to the technology (hardware & telephony) deployed on desks? • Is there a hot desk policy or do staff have their own desks? Will this change? • Are there any ‘equality impacts’ (e.g. for employees with a disability)? | • What procedures and guidance is available to staff that will need to be revised, removed or created? Will the scope of guidance available to staff change? • Will there be any changes to where or how people access procedures and guidance? Are procedures and guidelines documented and will this change? • Are there contingency procedures in place? How will these need to change? • Do procedures and guidelines differ across regions? Will this change? | • Are there changes required to legislation and/or policy? Are actions being taken to carry these out? | • Are there transitional ways of working that need to be introduced whilst only part of the organisation is using IPT? • Will there be changes in the interactions between staff who are operating new ways of working and those in other parts of UKBA? | • Will different management information need to be collected? • Are any other forms of MI captured currently? How will this change? • How will the MI reporting process change? • How will changes in MI affect staff? | • What contractual arrangements are in place currently? How will these be affected? • What Service Level Agreements (SLAs) are in place currently? How will these be affected? • Will additional SLAs or contractual arrangements be required? | • Will there be changes to the scope of service management support (including user help and support) and how it is provided? How will all the different types of user query be handled? • How will changes to user access requirements be managed? • How will solution changes be initiated by the business? • How will solution changes be communicated and implemented?
I.D. | Process Description | Change description (Who, why, what, when, where) | 0 = No Impact 1 = Low Impact 2 = Medium Impact 3 = High Impact | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same: | Impact: Mitigation / Change Action: Stop Doing: Start Doing: Do Differently: Do Same:
CIA0001 |  |  | 0
CIA0002 |  |  | 1
CIA0003 |  |  | 2
CIA0004 |  |  | 3
CIA0005 |  |  | 0
CIA0006 |  |  | 0
CIA0007 |  |  | 0
CIA0008 |  |  | 0
CIA0009 |  |  | 0
CIA0010 |  |  | 0
CIA0011 |  |  | 0
CIA0012 |  |  | 0
CIA0013 |  |  | 0
CIA0014 |  |  | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D3: 1 = Low 2 = Medium 3 = High

## SummaryChart
Ref | CHANGE | Applicant | Legal Rep | Caseworker | Correspondance team | Post room | Scanning team | [8 empty] | Note
CIA001 | Online application form | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH
CIA002 | Online payment | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM
CIA003 | Increased performance target | LL | MM | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH
CIA004 | Etc. | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH
CIA005 | Etc. | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH
CIA006 | Etc. | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH | HH
CHANGE IMPACT ANALYSIS Summary Chart
INSERT PROJECT TITLE
Business Owners:
TO BE REVIEWED
KEY TO SCORES/RATING:
HH
HM
HL
etc
This template uses:
‘likelihood’ (H,M, L) and
‘scale of impact’ (H, M, L)
GROUPS 'APPEARING' IN END-TO-END SOLUTION