## About
Business Change Readiness Assessment
These are matrix assessments of how ready the business operations are to proceed with planned changes.
They can be programmed at intervals approaching the proposed go live or roll-out.
The outputs from business readiness assessments inform the Go / No Go decision by the SRO or Project Board. (Not to be confused with assurance readiness assessments in advance of Gate reviews.)
The criteria for business readiness assessments will vary across projects and will need to be agreed with the key stakeholder groups.
The assessment should focus on the ‘deal breaker’ items and essential criteria to effect the change.
For example, it may not be necessary for the entire workforce to be trained on the new system by day 1 of a roll-out, the criteria being assessed may be 70% trained on day 1.
Thus, the readiness assessment will be related to the change plan but has a different focus and will not contain every element of the change plan
There are many ways to configure such an assessment according to complexity and scale of the project.
The principal is that it should be easily interpreted by the SRO and other decision makers and will give a view of progress at each periodic review in the closing stages of a project or phase.
Alternatively, at earlier stages, the management may find usefull, a broader assessment across the workforce and stakeholders.
Other tools can be used or developed according to such needs, such as the example below based on detailed survey and data capture sheets.
Example of an alternative, broader survey of people involved in the change

## Template
| Assessment Date: | ##/##/####
Name of Project Project Business Readiness Assessment
Ref. | Category | Readiness criteria | Success threshold | Must be complete by | Owner/ Responsible | Actions | Liklihood of meeting readiness criteria R,A,G or C (Complete) | Notes/Comments
Must be complete by
1 | [6 empty] | r
2 | [6 empty] | g
3 | [6 empty] | a
4 | [6 empty] | c
5 | [6 empty] | c
6 | [6 empty] | c
7 | [6 empty] | c
8 | [6 empty] | c
9 | [6 empty] | c
10 | [6 empty] | r
11 | [6 empty] | c
12 | [6 empty] | c
13 | [6 empty] | c
14 | [6 empty] | c
15 | [6 empty] | c
16 | [6 empty] | c
17 | [6 empty] | c
18 | [6 empty] | c
19 | [6 empty] | c
20 | [6 empty] | c
21 | [6 empty] | c
22 | [6 empty] | g
23 | [6 empty] | c
24 | [6 empty] | g
25 | [6 empty] | c
26 | [6 empty] | c
27 | [6 empty] | g
28 | [6 empty] | c
29 | [6 empty] | c
30 | [6 empty] | c
31 | [6 empty] | g
32 | [6 empty] | c
33 | [6 empty] | c
34 | [6 empty] | c
35 | [6 empty] | c
Assumptions

## ExampleBusinessReadinessMatrix
| Assessment Date: | ##/##/####
ABCD Project Business Readiness Assessment (Phase 1)
Ref. | Category | Readiness criteria | Success threshold | Must be complete by | Owner/ Responsible | Actions | Liklihood of meeting readiness criteria R,A,G or C (Complete)
|  |  |  | Must be complete by |  |  |  | Notes/Comments
1 | Approvals | All appropriate Project and Business Owners approvals obtained. | Business Readiness Assessment, 4 sessions held prior to go-live | 2018-03-06 | A. Nother |  | r
2 |  |  | Service Readiness Review approved | 2018-03-07 | B. Reddy |  | g
3 |  |  | Business Go/No Go decision made | 2018-02-28 | S.Porter - SRO |  | a | Included in the SRR Subject to SRR decision
4 |  |  | Project Board | 2018-02-26 | S.Porter - SRO |  | c
5 | Training and Guidance | User Guidance approved by Senior Business Representatives. | Agreed user guidance manual or help pages for the website written | 2018-03-06 | R. Seal | Draft to be completed by Lisa Car for review by Ron Seal | c
6 |  | User Guidance available to staff. Could be the training slides if approved. (Guidance document as used for the training courses) | All agreed guidance material available to users and any on line location communiated to all affected staff (Gray House and Manchester) | 2018-03-06 | T. Rainer | Draft to be completed by Lisa Car for review by Ron Seal | c
7 |  | Course outlines available for review | first complete drafts for all modules received by business area owners | 2018-02-03 | T. Rainer |  | c | Outlimes for all 3 courses received 13/02/2018
8 |  | Draft course materials reviewed | Remedial actions from review have been planned | 2018-02-13 | T. Rainer | Reviewing and adding relevent business context | c | Normal User course guidance complete and approved. Supplier delivered drafts late. Reviews ongoing for Sys Admin and BSU courses, including adding business context and scenarios.
9 |  | Course Material ready for training | Dry run of all training courses held | 2018-02-17 | T. Rainer | Supplier delay, now due to complete latest Tue 25 Feb | c
10 |  | Final training course materials approved | Final training course materials signed off by SRO, or delegated representative - RH | 2018-02-20 | R. Seal | Ron to assess after dry runs - Tue 25 Feb Awaiting decision on amendments to the Administrator course | r | Normal Users Training Dry run complete and approved. Super User and Admin courses to complete on Tue 25 Feb. Some updates to Super User and Admin guidance to be completed 28/02/2018.
11 |  | Training venues secured and security arrangements agreed at each venue for trainers | Gray House and Manchester training venues bookings confirmed andarragements made to give Supplier trainers access | 2018-02-13 | F.Ixit | Detailed actions in Training Handover note complete | c | 52 booking forms completed and submitted. Globe House confirmed to end Mar. Confirmation of Globe availability after March still required
12 |  | Training equipment installed and configured (projectors, scanners) | Training rooms ready for courses for Gray House and Manchester Users | 2018-02-20 | F.Ixit | SF to check with Rob, to confirm after dry runs | c
13 |  | Training schedule agreed | Final Training Schedule agreed with the senior Business users | 2018-01-24 | R. Seal |  | c
14 |  | Trainers attendance confirmed | Trainers (Blackthorn) named, booked and confirmed, for Beckett Hse and Dover | 2018-02-13 | F.Ixit |  | c
15 |  | BSUs attendance confirmed | BSUs named, booked and confirmed, for Beckett Hse and Dover | 2018-02-13 | F.Ixit |  | c
16 |  | Business representative appointed to manage the training attendance | invitations to delegates issued, Attendees provided with access to the CIDRE training environment, min for Beckett Hse and Dover | 2018-02-13 | R. Seal | superusers to undertake tng module to take on after first few courses. G. Wilde to set up the first few on system. | c
17 |  | Staff and Managers trained | Two thirds of users trained for Beckett House and Dover (including all super users for that site) | 2018-03-06 | R. Seal |  | c
18 | Operational Support | Ongoing support arrangements/plan approved | Business Support Group T.O.R. Agreed and group has been established | 2018-03-06 | R. Seal |  | c | Draft TOR under review by SRO, awaiting feedback
19 | Business Processes | Confidence that the business solution will support the business process nationally, accross all locations. | Users workshop completed and any proposed recommendations acted upon. | 2018-02-20 | B. Reddy | Set-Up mini forum for local users. National forum, mid Mar | c | Forum held 21 Feb Gray Hse. Further forum for other areas to be arranged for mid Mar. Evaluation of Gray and Manchester business processes to be formulated and scheduled
20 |  | Users are aware of the requirement to work with new and old systems for existing cases during the transition period | Guidance prepared and distributed. | 2018-03-06 | B. Reddy | Draft to be completed by Lisa Car for review | c
21 |  | Essential system functionality such as, Search and Special Handling minimum requirements met | Senior Business User assesses that BAU process will not be compromised. | 2018-03-06 | B. Reddy | F.Ixit carrying out testing. Ron negotiating for additional sprints | c | Issues with disclosure report and other minor bus to be resolved
22 | Business Area Readiness | Hardware configured and available to enable new operations to be carried out effectively | Scanning capability in place and operational at Beckett Hse and Dover with an implementation schedule agreed for the other sites | 2018-03-06 | B. Reddy | Ron to provide site contact names, required by supplier | g | Ron in contact with suppliers, accepted up to 1 week delay after first go-live. Gray House Scanner delivery booked for 10 Mar.
23 |  |  | All users provisioned with scanning capability. User instructions available for scanning | 2018-03-06 | B. Reddy |  | c
24 |  |  | Laptops with internet access issued to any users requiring mobile access to System, where deemed essential for Gray House and Manchester users. | 2018-03-06 | B. Reddy | R. Seal to confirm the requirement. Users emailed | g
25 |  | Business Areas have been made aware of implications of new system working arrangements and have had opportunity to make appropriate adjustments | users appraised of impact on their areas, with an appropriate feedback loop | 2018-02-20 | B. Reddy |  | c
26 |  | New ways of working communicated with external stakeholders (e.g. Police) where there is an impact on them | All new ways of working assessed for impact on external stakeholders External Stakeholders informed of changes and impacts. This will be localised liaison due to the wide variation in working practices. | 2018-03-06 | B. Reddy |  | c | 1st workshop planned for 21 Feb
27 | Stakeholder Communications | Business users informed of how their work is affected by the release and the impact on their role. | All new ways of working assessed for impact on staff and their roles Staff informed of changes and impacts | 2018-03-06 | A. Nother |  | g | workshop held 21 Feb
28 | Stakeholder Communications | Communications Plan agreed | Actions accepted by business representative | 2018-02-13 | A. Nother |  | c
29 | Stakeholder Communications | Communications plan being delivered | Weekly assessment at Business Readiness checkpoint | 2018-03-06 | A. Nother | GH off Sick, RH and JH to monitor Mailbox MB sending course details out | c
30 | User Provisioning | System Provisioning arrangements agreed | Supplier has agreed to provision all users who have attended training Supplier to set up users until first system Admins are Trained | 2018-02-13 | A. Nother |  | c | Sys Admins set up new users
31 |  | Users Provisioned on system and users informed. | Supplier confirms Gray House andManchester users are able to access the supplier System from go-live date | 2018-03-06 | A. Nother |  | g
32 |  | Business rules for users access to system have been agreed | Rules documented and approved | 2018-02-20 | A. Nother | D. Knott to approve Business Support Group TORs | c | Draft rules to be approved by SRO
33 |  | BAU provisioning for changes in role and new users available | BAU arrangements in place and Business areas informed of BAU arrangements | 2018-03-06 | A. Nother | D. Knott to approve Business Support Group TORs | c
34 | Business Contingency | Business roll-back plans considered and can be implemented | Business Continuity plans reviewed within the business and any changes made to take account of new ways of working, including possible work around in event of roll-back | 2018-03-06 | B. Reddy |  | c
35 | Transition Plan | Address all Transition Plan Phase 1 activities with respect to Gray House and Manchester | Approval of Business Readiness Final Assessment | 2018-03-06 | P.Lanner |  | c
Assumptions
• There will be a separate Business Readiness Assessment as a separate activity for the Phase 2 go-live. • This readiness assessment is being conducted proximate to the first go-live sites for users at Gray House and Manchester. • No separate readiness assessments are intended for subsequent go-live sites in the phase 1 roll-out. • There is no Minimum MI requirement for the initial go-live, despite the earlier understanding that bespoke MI would be included in the supplier product. • Re-working of External Procedures do not need to be finalised for phase 1 go-live, but will need to be updated for Phase 2 implementation. • No requirement to re-configure accommodation for working with new system. • Existing print facilities at will be sufficient for new system print requirements. • Specific Impacts on unique NI and Scotland processes will be assessed separately prior to their go-live.