## Sheet1
Key Benefits Management Statements | Always | Usually | Occasionally | Never | Suggested Potential Actions
The benefits from our change initiative(s) are clearly identified in measurable terms that demonstrate strategic contribution. |  |  |  |  | Benefits-led change ('start with the end in mind); driver based analysis; benefits mapping; customer insight; start gate.
Benefits forecasts are robust and realisable. |  |  |  |  | Reference class forecasting; stochastic forechasting; Delphi technique; conversion ratios; sensitivity and scenario analysis; booking the benefits; pre-mortems.
Benefits are expressed and quantified consistently by all change initiatives, thereby enabling reliable portfolio prioritisation. |  |  |  |  | Portfolio benefits management framework including beneftis eligibility rules; decision conferencing.
Responsibilities are clearly defined for realising each benefit and for delivering the business and enabling changes on which benefits realisation is dependent. |  |  |  |  | Benefits profile and benefits realisation plan; booking the benefits.
We don't stop at the hurdle rate of return, but instead look for all potential benefits. |  |  |  |  | The 'dog that didn't bark' test; benefits categorisation framework; benefits opportunity management.
The investment rationale and value-for-money position is tested on a regular basis with further recommitment to benefits realisation so that there are no 'orphan' initiatives. |  |  |  |  | Stage / phase gates with staged release of funding; benefits contracts
Measures used provide a 'rich picture' on benefits realisation, and rather than encouraging perverse incentives they engage the user in exceeding forecast. |  |  |  |  | Suite of leading and lagging measures, proxy indicators, evidence events, case studies, surveys and stories.
Benefits realisation is monitored on an active basis with prompt corrective action being taken to address emerging shortfalls and to mitigate known and emergent dis-benefits. |  |  |  |  | Benefits dashboard reporting; 'management by exception'; 'one version of the truth'; 'clear line of sight' reporting.
Effective action is taken to identify and leverage emergent benefits. |  |  |  |  | Ongoing participative stakeholder engagement; benefits opportunity management.
Checks are undertaken to assess whether the performance matched the promise and to identify and apply lessons learned. |  |  |  |  | Formal post-implementation and post-investment reviews; deep-dive reviews.