## Overview
PMO Threshold Tool
Welcome to the Programme Management Threshold Tool. This tool has been created to help you to understand the support needed to run a project and the level of assurance required, and is to be used as a starting point for a conversation with your Programme Management Office (PMO). You will be asked to identify the statements that best reflect your project - you can complete it collectively with your project board and or individually to be then verified by the project's senior responsible owner. You should regularly review your responses: if they change over time you will need to reconsider the support and assurance required.
Your project:
Your name:
You title:
Your email:
Date completed:
Optional verification:
Name of verifier:
Date verified:
© Local Partnerships LLP 2023

## Scoring
Project Scoring Sheet
Category and Criteria | Value
Value and status
What is the value of your project? Show the total financial value to the project (e.g. capital or total contract value if a procurement).
What is the status? Is the project part of the established delivery plan of the council?
Complexity
Timescale. How long will it take until the project is completed from start to finish and, where relevant, the resulting service up and running?
Internal partners. Does the project have shared ownership or significant involvement of another directorate? This does not include corporate functions delivering assurance or due diligence duties.
External partner. Are you working with another stakeholder? This does not include suppliers.
Funders. Are there responsibilities to funders which make the project more complex?
Risk
Service. Is there a risk that non-delivery would have an impact on communities and individuals?
Reputation. Is there a risk to the council's reputation and standing?
Capacity
Capacity. What capacity is needed to deliver the project?

## Results
Project Score
Total overall score = 0 / Low
1. Intense
2. High
3. Medium
4. Low
Self-serve through guidance and tools, assurance via the directorate
Project management support and PMO assurance

## Calculations (hidden)
Category | Question | Option | Score
Value and status | Q1. What is the value of your project | 0
Value and status | Q2. What is the status? | 0
Complexity | Q3. How long the project runs, which can also be the length of a procurement | 0
Complexity | Q4. Internal partners | 0
Complexity | Q5. External partners | 0
Complexity | Q6. Funders | 0
Risk | Q7. Service | 0
Risk | Q8. Reputation | 0
Capacity | Q9. Capacity | 0
Scoring Totals | Combined Score | Max Score
Value and status |  | 16
Complexity | 0 | 16
Risk |  | 16
Capacity |  | 16
Total | 0 | 64
Min | Max | Categorisation
48 | 64 | Intense
32 | 48 | High
16 | 32 | Medium
0 | 16 | Low
0 | 64 | Total
Score Outcome: | Low
Total overall score = 0 / Low

## List (hidden)
Category | Question | Option | Score
Value and status | Q1. What is the value of your project
Value and status | Q1. What is the value of your project | Between £0 and £49,999 | 1
Value and status | Q1. What is the value of your project | Between £50,000 and £99,999 | 2
Value and status | Q1. What is the value of your project | Between £100,000 and £249,999 | 3
Value and status | Q1. What is the value of your project | Between £250,000 and £999,999 | 5
Value and status | Q1. What is the value of your project | Between £1m and £2.99 million | 6
Value and status | Q1. What is the value of your project | Between £2.5m and £9.99 million | 7
Value and status | Q1. What is the value of your project | £10 million and over | 8
Value and status | Q2. What is the status?
Value and status | Q2. What is the status? | Not within any plans | 1
Value and status | Q2. What is the status? | Part of an agreed directorate or service plan | 3
Value and status | Q2. What is the status? | Listed as one of the council's transformation projects | 4
Value and status | Q2. What is the status? | Project in the corporate plan or corporate delivery plan | 6
Value and status | Q2. What is the status? | The project is agreed in the capital programme | 8
Complexity | Q3. How long the project runs, which can also be the length of a procurement
Complexity | Q3. How long the project runs, which can also be the length of a procurement | Project lasts under 6 months | 1
Complexity | Q3. How long the project runs, which can also be the length of a procurement | Project run for 6 months to a year | 2
Complexity | Q3. How long the project runs, which can also be the length of a procurement | Project runs for 1 - 2 years | 3
Complexity | Q3. How long the project runs, which can also be the length of a procurement | Project runs for over 2 years | 4
Complexity | Q4. Internal partners
Complexity | Q4. Internal partners | Single service involved | 1
Complexity | Q4. Internal partners | More than one service involved in a single directorate | 2
Complexity | Q4. Internal partners | Significant involvement of more than one directorate | 3
Complexity | Q4. Internal partners | A whole council project | 4
Complexity | Q5. External partners
Complexity | Q5. External partners | Solely a council project with no other external partner involved | 1
Complexity | Q5. External partners | External partners as stakeholders, but not needing to be involved the project delivery | 2
Complexity | Q5. External partners | External partners requiring involvement in the project's delivery | 3
Complexity | Q5. External partners | Having to manage more than 2 external partners involved in project delivery | 4
Complexity | Q6. Funders
Complexity | Q6. Funders | All council funding with no other funding source | 1
Complexity | Q6. Funders | Funded project, but low reporting or part of regular funding | 2
Complexity | Q6. Funders | One external funder that requires regular reports based on their criteria | 3
Complexity | Q6. Funders | More than 2 different funders requiring regular reports with different criteria | 4
Risk | Q7. Service
Risk | Q7. Service | If not delivered would have little impact of services, more of a nice to have | 1
Risk | Q7. Service | If not delivered would cause impact to services | 3
Risk | Q7. Service | If not delivered would impact on social and economic benefit to the community | 5
Risk | Q7. Service | If not delivered would affect the council's statutory duties | 6
Risk | Q7. Service | If not delivered would cause essential service to fail vulnerable residents | 7
Risk | Q7. Service | If not delivered would cause harm to people | 8
Risk | Q8. Reputation
Risk | Q8. Reputation | Low reputational risk | 1
Risk | Q8. Reputation | Reputational risk internally felt | 3
Risk | Q8. Reputation | High reputational risk felt locally | 4
Risk | Q8. Reputation | Reputational impact profiled at a regional level | 6
Risk | Q8. Reputation | High reputational risk with national impact | 8
Capacity | Q9. Capacity
Capacity | Q9. Capacity | The services has capacity to run this project | 1
Capacity | Q9. Capacity | The services could do with some light project management support | 5
Capacity | Q9. Capacity | The service has no capacity to run this project and needs support due to the high risk | 16
Project Board / colleague / line manger / external partner
Project board
Colleague
Line manager
External partner