# Business Case – Service Statement

To ensure your Service Statement makes a strong case it is crucial that you follow the guidance at the bottom of this document. This will make the process more streamlined and easier for the Business Development Group to review.

Please complete every section of the form as outlined below.

| Date Completed |  |
| --- | --- |
| Title of Scheme |  |
| Reference |  |
| Project Manager |  |
| Directorate |  |
| Contact Officer |  |

Please indicate by typing the name of your sponsor/partner in the below boxes that you have completed these actions. Actions 3 and 4 may not apply to you.

| I have confirmed Sponsor Support at Leadership / Assistant Director Level from: | + |
| --- | --- |
| I have presented the proposal and have approval from the appropriate Senior Management Team to progress; the following Senior Management Team are in support of the proposed project: |  |
| I have received confirmation that the Financial Implications within this Form are accurate, and that there is Financial Resource to support the project; this has been confirmed by: |  |
| If there is a need to consider Procurement Implications, I have confirmed the framework I will be using with a member of Procurement and have confirmed that they have resource to support the project within the given timeframe; I have confirmed these things with (please state N/A if not applicable): |  |
| I have completed the “Subsidy Control limb Assessment Template” and submitted it with the BCSS. (please state N/A if not applicable): |  |
| I have discussed any potential Legal implications (including Subsidy Control) with a member of Legal Services and have confirmed that the Team have resource to support the project within the given timeframe; I have confirmed this with (please state N/A if not applicable): |  |
| It’s been established that the Subsidy Control seven principles need to be assessed and so I have also submitted “Subsidy Control Principles Assessment” for consideration with the BCSS. (please state N/A if not applicable): |  |
| I have discussed any potential Human Resources implications with a member of the People and Culture Team, and have confirmed that the Team have resource to support the project within the given timeframe; I have confirmed this with (please state N/A if not applicable): |  |
| I have discussed any potential IT implications with a member of IT Services, and have confirmed that the Team have resource to support the project within the given timeframe; I have confirmed this with (please state N/A if not applicable): |  |
| I have discussed any potential Estates / Property Implications with a member of Estates and Business Development Team, and have confirmed that the Team have resource to support the project within the given timeframe; I have confirmed this with (please state N/A if not applicable): |  |
| If required, I have discussed project support with a member of the Strategy, Policy, and Performance team, and have confirmed that the Team have resource to support the project within the given timeframe; I have confirmed this with (please state N/A if not applicable): |  |
| I have discussed any potential environmental implications, such as Biodiversity Net Gain, with a member of the environmental sustainability team and have confirmed that the team have resource to support the project within the given time frame. I have confirmed this with (please state N/A if not applicable): |  |
| I have completed the “Equality and Diversity Impact Assessment (EIA)” and submitted it with the ITS. (if you do not consider that an EIA is required, please state why) |  |
| Type of Scheme (is this Capital, Revenue, Commercial, External Funding or other, please specify): |  |
| If this is an external funding opportunity, I established with the grant paying department whether the conditions of the grant require certification on the use of the grant. If it will require certification, I am engaged with the Audit Team to ensure sufficient time for certification; the member of the Team I have confirmed the proposal with is (please state N/A if not applicable): |  |

- Background, Scope, and Purpose

- Strategic Case (Include here any information about the Council priorities, the use of qualitative and quantitative research data/ insights evidence, links to policies, social value outcomes, and climate change and the environment)

- Economic Case

- Commercial Case

Optimising Income Generation (NNDR, Council Tax, Other, etc.):

Details of the procurement process that will be followed:

- Option Appraisal

Details of options considered and reasons for the preferred option being selected (i.e. value for money, return on investment, etc):

- Governance and Management Case

- Key Scheme Milestones, Dependencies and Timelines:

- Evidence of team / Board arrangements in place, and detail of the involvement from different workstreams:

- Evidence of detailed project plan and project management tools in place:

- Decisions required (i.e. Planning permission, Cabinet, Funding bid approval, etc.):

- Previous successful project delivery

- Evidence of appropriate project management skills required:

- Risks, Barriers, Opportunities (Including any mitigating actions) and Impact Assessment

- Strategic Risks

- Financial Risks

- Delivery Risks

- Reputational Risks

- Exit / Abortive Strategy for this Project

- Insurance Risks

- Impact Assessment

- Stakeholders – Evidence of Engagement – Including level of commitment / feedback and details of any activity undertaking in line with the Engagement Strategy

- Engagement with political stakeholder (e.g. Members, Portfolio Holder, Cabinet) that has taken place for this scheme:

- Engagement with internal stakeholders (e.g. Finance Business Partners, Legal, People & Culture, Service Area, Director, Leadership Team) that has taken place for this scheme (if applicable – evidence that pre-application advice has been sought from planning)

- Engagement with external stakeholders (e.g. partnership agencies, regulatory bodies, technical experts, service users, voluntary sector organisations, community representatives, public, potential users) that has taken place for this scheme:

- Financial Case

  - Please populate the “BDG Finance Template (CY +3yrs)”and submit the completed spreadsheet with the BCSS.

Accurate profiling is required, only request funding in the year that it is required.

9.2 Financial Assumptions

9.3 Revenue Implications

9.4 VAT Implications – See Guidance Notes

### If your capital project expenditure is forecast to be £100,000 (including VAT) or more, please complete the below section. ### North East Lincolnshire Council can reclaim VAT on purchases (input tax) relating to VAT Exempt income providing that the council's input tax relating to exempt income/supplies is less than 5% of the total input tax for each financial year. ### If the total amount of input tax is more than 5%, the council is liable to repay the total amount of input tax relating to exempt income. This presents a significant cost to the council. Potential sources of Exempt income include (but are not restricted to), Land or property, community and neighbourhood centres, parks and open spaces, burial and cremation, education and cultural services. For VAT implications guidance on capital project forecast expenditure of £100,000 (including VAT) or more, please *contact the Governance Specialist by email; FINNELCVAT@nelincs.gov.uk, providing a copy of the project brief. The Governance team aim to review VAT queries promptly, however, please allow 10 working days response time following the submission of the project brief to FINNELCVAT@nelincs.gov.uk. Please highlight the number below that applies to your project: - The VAT implications have been evaluated and will not impact on the council’s VAT recovery - The VAT implications have been evaluated and may impact on the council’s VAT recovery

In the box below please provide further details of how the impact could be avoided e.g., Option to Tax considered?

GUIDANCE FOR COMPLETING BUSINESS CASE SERVICE STATEMENTS

The Business Development Group (BDG) will lead the prioritisation process for the capital programme and other significant business cases. Given the significant reduction in the scale of our capital investment and the clear direction for the council, prioritisation will be essential going forward. Prudent investment will require that one-off investment projects must be considered against all other investment requirements and the available resources.

All Business Case Service Statements (BCSS) will be put through an appraisal process that will consider the financial, strategic, economic, and commercial case of the project. It will assess the value for money afforded from the proposed project and the BCSS will be scored and prioritised. The BCSS will then be taken to Leadership for approval and, if a key decision is required, to Cabinet. Please see the scoresheet used by the BDG to appraise each scheme. The below advice outlines the key information required as part of the completion of the BCSS:

- Background, Scope, and Purpose

- A clear description of the scheme, with acronyms explained

- Details of all partners involved and the nature of their involvement

- Details of assets created (new build, replacement, equipment, refurbishment etc.)

- Where is the project located?

- Who will use/benefit from the project (service users, partners, internal, businesses etc.) and how you have consulted and engaged with as many people as possible to ensure that the proposed approach is the best way forward?

- Details of services it supports

- Strategic Case

- Describe how the project will contribute to the Council Plan

- Describe the impact it will have on stronger economy and stronger community

- Detail any strategy or policy the project is linked to (a full list of policies / strategies is available at the following web page: www.nelincs.gov.uk/council-information-partnerships/policies-and-strategies/).

- Detail how you have consulted and engaged with communities that will be affected by the project in line with the requirements of the Engagement Strategy.

- Ensure that the use of data and insight research is evidenced, with support/ guidance from the strategy, policy and performance team - strategypolicyandperformanceteam@nelincs.gov.uk. Further details on the work of this team can be found using the link Strategy, Policy & Performance - Home (sharepoint.com).

- Detail any known or potential Social Value outcomes that may be achieved through the project (further information and the Social Value policy can be found by searching for Social Value on the Intranet).

- Explain any climate change and environmental implications. All projects must consider the impact of the proposal on climate change and the environment. This should include reference to the Council’s environmental policy and how the proposal supports the Council’s environmental priorities:

  - By leading North East Lincolnshire towards consuming resources more efficiently, eliminating waste and supporting & developing the green economy & infrastructure.

  - By recognising and realising the economic and social benefits of a high-quality environment.

  - By working towards a low carbon North East Lincolnshire that is prepared for, and resilient to, the impacts of climate change.

How does the scheme link with the Council’s priorities/duties, and how does it link with the Business Delivery and Commissioning Proposal?

This section should provide information regarding:

- How the project will have an impact on the following outcomes / priorities: creating a stronger economy and creating stronger communities.

- How the project is fulfilling any duties of the Council.

- How the project links to any existing policies and strategies.

- How the project links to the Business Delivery and Commissioning Proposal.

How does the scheme link with the Council’s Social Values?

Social Value involves looking beyond making decisions based on financial costs and instead at the wider benefit to a community.

It is about getting the most social, environmental, and economic value when the authorities’ money is being spent on making North East Lincolnshire a better place.  For instance, making sure local people get jobs when money is spent on new building schemes, or bringing businesses to the area that reinvest some of their profits back in other service in the community, are just two examples.

Therefore, this section should provide information regarding:

- How the project will provide the area with social, environmental, and economic value.

- How the project links to the Council’s Social Values.

For more information in relation to Social Values please follow the link  – Social Values

- Economic Case

- Details of any business-related impact on the council or the community such as jobs, skills, employment, supporting business.

- Details of how individuals might be supported such as reducing the need for intervention by us or partners.

- Details of social benefits for example reducing crime, improving education etc.

- Commercial Case

- Details of how it might help support external business increasing or maintaining NNDR (national non-domestic rates, also referred to as business rates) receipts.

- Optimising income through generating New Homes Bonus grant or increasing the Council tax base.

- Details of the procurement, to include the planned procurement procedure and route to market, any Preliminary Market Consultation undertaken to inform your route to market and how you will comply with the CPRs (contract procedural rules) and achieve value for money.

- Option Appraisal

- Describe other delivery options you have considered and why you have discounted them.

- Details of the preferred option and why it has been choses (i.e., value for money, return on investment, response to community engagement and consultation etc.)

- Need to state why NELC are the best organisation to take the project forward.

6 	Governance and Management Case

6.1	Key Milestones, Dependencies and Timelines

- All key milestones must be included with a timeline. This must include start and end date. This will be used to assess how ready the project is to commence.

- Key people responsible for delivery of the milestones.

- All dependencies must be highlighted; these should include acquisition, planning, contracting, procurement, design, feasibility, partner agreements, funding sources etc.

  - Evidence of team / board arrangements in place:

- State the controls in place to monitor project progress, including any partner or community representation.

- Governance arrangements including any Boards that progress is reported into both internal and external.

- Detail the reporting framework for the project (this must be in accordance with corporate procedures)

6.3      Evidence of a detailed project plan:

- Provide evidence of the stages that the project needs to go through in order for delivery to be on time and to budget.

6.4      Decisions Required:

- Please detail any decisions which are required prior to the project being able to start. E.g., Cabinet decision, funding award etc.

  - Previous Successful Delivery

- A track record in delivering projects is important, please provide a brief statement about previous successful delivery which demonstrates that delivery has been on time and to budget

- Please provide evidence of ability to commence with project

6.6	Evidence of appropriate project management skills required

- Please provide any details of project management qualifications or experience of managing projects in the past.

7	Risks, Barriers and Opportunities and Impact Assessment

7.1	Strategic risks

Strategic risks need to be clearly identified (if approved any strategic risk will need to be assessed and included on the corporate register)

7.2	Financial risks

Financial risks need to be clearly assessed, this should include such things as delivering to budget, securing funding, cost increases, sustainability of savings etc.

7.3	Delivery risks

Delivery risks need to be clearly assessed, this should include such things as securing permissions, sale/purchase agreements, contracting risk, partner delays etc…Please note that we have a lot of projects that say that they are ready for immediate start but then do not spend for 12 months or more – we need to make the best judgement on the information provided and make the best use of corporate resources so please provide a realistic not optimistic start date.

7.4	Reputational risks

Reputational risks need to be clearly assessed; this should include such things as consultation with members, community response, consideration of local stakeholders etc.

7.5	Exit / Abortive Strategy

What is the exit / abortive strategy if the project becomes unsustainable and how associated costs will be met.

7.6	Insurance risks

Capital schemes potentially have insurance implications.  They can add to the overall cost of the Council’s insurance premiums, there is a need to ensure that contractors have adequate public liability and/or professional indemnity insurance, and the revenue implications  should the asset be subsequently damaged  given the Council’s levels of self- insurance  (buildings £100K, public liability 75K).   Please visit the insurance wiki page, or email insurance at insurance@nelincs.gov.uk.

7.7	Impact assessments

Impact assessments are simply a way to help us think about what might happen if we do something and they can reveal positive opportunities as well as risks. Three key areas of impact should be considered. These are: Equality, Data Protection and Strategic Environmental Assessments. The following link provides more information on what should be included in this section: https://nelincsgovuk.sharepoint.com/sites/WikiHub/SitePages/Impact-Assessments.aspx

8	Stakeholders – Evidence of Engagement – including level of commitment / feedback

Where applicable the following stakeholders must be considered:

8.1	Political Stakeholders

Engagement with political stakeholders (e.g., Members, Portfolio Holder, Cabinet) that has taken place to establish the need for the scheme

8.2 	Internal Stakeholders

Engagement with internal stakeholders (e.g., Service Area, Director, Leadership Team) that has taken place to establish the need for the scheme (if applicable – evidence that pre-application advice has been sought from Planning).

8.3	External Stakeholders

Engagement with external stakeholders (e.g., Partnership Agencies, Regulatory Bodies, Technical Experts, Service Users, Voluntary Sector Organisations, Community Representatives, General Public, Potential Users) that has taken place to establish the need for the scheme.

Engagement with the community should be in line with the expectations outlined in the Engagement Strategy https://www.northeastlincolnshireccg.nhs.uk/data/uploads/engagement-strategy/twlt-final-digital-a11y-accessible.pdf

For all categories of stakeholder, the following details should be included:

- Details of engagement with stakeholders including who, how, when and the results of the discussions that took place.

- How this informed the design and need for the project.

- Evidence that key stakeholders have/will commit to the project.

9	Financial Case

  - Financial Spreadsheet

The information input will form part of the financial assessment of the Business Case - it needs to be as accurate, robust and complete as possible. It is this information that will support the inclusion of the project in the programme and must stand up to scrutiny.

| BDG Finance Template |  |
| --- | --- |

  - Financial Assumptions

- For each section completed you need to include information as to how you have arrived at the financial information and what assumptions you have made.

- Where you have included funding other than from corporate capital you must detail the source and nature of the funding. For a revenue contribution you must state where the revenue budget is located, for any grant funding you must include information on awarding body, if the grant is ring fenced, at what stage the grant is at (application, approval etc.), for S106 agreement (this mitigates the impact of the development on the local community and infrastructure) it must be identified if this has been received, for partner or other contribution details of the status of the agreement (verbal, agreed at board, contract etc.)

- Details of the savings and where they will be realised from.

- Information on any potential capital receipt generated.

  - Revenue Implications

If there are revenue implications of the project either one off or on-going you must identify how this is to be funded for example an existing revenue budget, a future pressure/opportunity that needs to be highlighted in the Medium-Term Financial Plan if successful. Any future income streams need to have assumptions evidenced.

  - VAT Implications

- North East Lincolnshire Council can reclaim VAT on purchases (input tax) relating to VAT Exempt income providing that the council's input tax relating to exempt income/supplies is less than 5% of the total input tax for each financial year. If the total amount of input tax is more than 5%, the council is liable to repay the total amount of input tax relating to exempt income.  This presents a significant cost to the Council.

- Potential sources of Exempt income include (but are not restricted to), Land or property, community and neighbourhood centres, parks and open spaces, burial and cremation, education, and cultural services.

- For VAT implications guidance on capital project forecast expenditure of £100,000 (including VAT) or more, please contact the Specialist by email; FINNELCVAT@nelincs.gov.uk, providing a copy of the project brief.

Additional Information

- Corporate Parenting

Corporate Parenting is a term that described local agencies accountability for discharging responsibilities towards children and young people in and leaving the care of the Local Authority.

When a Local Authority starts to care for a child, young person, the Council has a legal responsibility to share the duties and responsibilities of the child’s parents. Because many different people carry out the work of the Council, it is known as “Corporate Parenting”.

For more information in relation in relation to Corporate Parenting please review the document below:

| Corporate Parenting Information |  |
| --- | --- |

- Equality and Diversity Impact Assessment

The assessment ensures as an authority we meet our duties to recognise value and promote the diversity of people and ensure they have equal opportunities to access and receive services. The duty involves 9 protected characteristics as follows:

  - Age

  - Disability

  - Gender Reassignment

  - Marriage and Civil Partnership

  - Pregnancy and Maternity

  - Race

  - Religion or Belief

  - Sex

  - Sexual Orientation

For more information in relation to the Equality and Diversity Impact Assessment, as well as the link to the form please following the link – EIA

- Subsidy Control

The Subsidy Control rules determine the lawfulness of awards of financial assistance made using public sector resources and given to business and other organisations engages in economic activity.

For more information and guidance in relation to Subsidy Control please find the “Statutory Guidance for the UK Subsidy Control Regime” below, as well as the “Limb Assessment” form for completion:

| Statutory Guidance for the UK Subsidy Control Regime |  |
| --- | --- |
| Subsidy Control – Limb Assessment |  |